## Slide 1: FY 2024 BUDGET PREPARATION CALENDAR AND SUBMISSION REQUIREMENTS
Junaid Ibne M. Karim
Acting Division Chief
BMB-E

## Slide 2
OVERVIEW OF THE BUDGET PREPARATION PHASE
PRE-BUDGETING STAGE
SUBMISSION OF BUDGET PROPOSAL AND ACTUAL OBLIGATION
CONDUCT OF TECHNICAL BUDGET AND EXECUTIVE REVIEW BOARD HEARINGS
BUDGET FINALIZATION, PRINTING AND SUBMISSION

## Slide 3
Issuance of the Budget Call
Conduct of Budget Forum for National Government Agencies and Government Corporations
Consultations with: RDC (with ACOs/AROs), CSOs, Student/Faculty Associations, PASUC, and Other Stakeholders
Calendar of Activities
JANUARY
JANUARY
FEBRUARY

## Slide 4
Coordination between Agency Central Offices (ACOs) with their respective Agency Regional Offices (AROs) shall be undertaken:
AROs shall craft annual regional plans and budgets anchored to the national priorities
Agency programs to be implemented by LGUs shall have been coordinated with the targeted LGUs
ACOs shall provide timely feedback to the RDCs on the items that were and were not included in the submitted proposals.

## Slide 5
Encoding and submission
(thru OSBPS v2.0) of:
FEBRUARY 1 – APRIL 28
FY 2022 Actual Obligations
FY 2022 – 2026 Revenue Program
Calendar of Activities
APRIL 14
Issuance of NBM for Budget Priorities Framework
APRIL 17 –
MAY 15
Conduct of Technical Budget Hearings
Encoding (thru OSBPS v2.0) of FY 2024 Budget Proposals
Submission of signed hard copies

## Slide 6
Conduct of Executive Review Board (ERB) Hearings
Sending of Confirmation Letters to Agencies of the Total Budget
Levels
(Tiers 1 and 2)
Presentation to the President and the Cabinet of the FY 2024 Proposed
Budget Levels
Calendar of Activities
MAY 26 –
JUNE 8
JUNE 13 - 14
JUNE 20 / 21

## Slide 7
JUNE 23 –
JULY 1
Finalization of
FY 2024 Budget Documents
(i.e., NEP, BESF Tables, Staffing Summary and President's Budget Message)
Calendar of Activities
JULY 1 - 17
Printing of the Budget Documents
JULY 20
Submission of the Budget Documents to the President

## Slide 8
Calendar of Activities
JULY 24
Submission of the President's Budget to Congress
Same day as the 2023 State of the Nation Address

## Slide 9
ACTIVITIES WITH REVISED SCHEDULE
ACTIVITY | FROM | TO
Encoding and submission (thru OSBPS) of Past Year's Actual Obligations and FY 2022 - 2026 Revenue Program | February 1 - April 28, 2023 | January 23 - April 28, 2023
Issuance of NBM for Budget Priorities Framework (BPF) | April 14, 2023 | 3rd week of March 2023

## Slide 10
ACTIVITIES WITH REVISED SCHEDULE
ACTIVITY | FROM | TO
Encoding and submission of all BP Forms of FY 2024 Budget Proposals (thru OSBPS) Details of Tier 1 (FEs) and Tier 2 (New Spending) | April 17 - May 15, 2023 (29 days) | 4th week of March – April 30, 2023 (35 days)
Submission of signed hard copies of FY 2024 Budget Proposals |  | 
Conduct of Technical Budget Hearings for Tier 2 (New Spending) Proposals, including PCB |  | 

## Slide 11
SUBMISSION DEADLINE
Budget Preparation Forms for the:
FY 2022 Actual Obligations; and
FY 2022-2026 Revenue Program;
NO EXTENSION

## Slide 12
REVISED SUBMISSION DEADLINE
All Budget Preparation Forms for the FY 2024 Budget Proposals (Tiers 1 and 2)
NO EXTENSION

## Slide 13
Submission requirements
1
2
Budget proposals of departments/
agencies belonging to the education sector should cover those activities to be implemented within the Calendar Year (CY) 2024 (i.e., January to December 2024 only) irrespective of the Academic year
For budget proposals of agencies involving specific concerns, the endorsement of pertinent departments/agencies/
entities is required.

## Slide 14
Submission requirements
ENDORSING ENTITY | SUBJECT OF ENDORSEMENT
CHED | SUCs Budgets
DA | Research and Development (R&D) in Agriculture and Fisheries
PSA | Systems of Designated Statistics pursuant to E.O. No. 352
DOST | R&D in natural resources, environment, technological and engineering sciences
DENR-NAMRIA | Procurement of data from airborne and spaceborne platforms and other related products and services for mapping purposes
ICF Review Panel | Funding proposals pertaining to the Hosting of International Conferences

## Slide 15
Submission requirements
ENDORSING ENTITY | SUBJECT OF ENDORSEMENT
NEDA | New infrastructure projects as covered by approved Three-Year Rolling Infrastructure Program (TRIP) and Public Investment Program (PIP)
OPAPRU | Payapa at Masaganang Pamayanan (PAMANA) Program
DICT | Information Systems Strategic Plan (ISSP) in support of ICT-related proposals
OEO-PhilSA | R & D of space science and technology applications (SSTAs) & Procurement of data from spaceborne platforms
lAEECC (DOE as secretariat) | Government Energy Efficiency Projects

## Slide 16
Submission requirements
1
2
3
Budget proposals of departments/
agencies belonging to the education sector should cover those activities to be implemented within the Calendar Year (CY) 2024 (i.e., January to December 2024 only) irrespective of the Academic year
For budget proposals of agencies involving specific concerns, the endorsement of pertinent departments/agencies/entities is required.
Budget proposals of participating agencies that form part of convergence programs and projects shall be limited only to the specific priority programs and projects of a PCB duly coordinated with the lead agencies.

## Slide 17
Submission requirements
5
6
7
The required submission modality shall be via the Online Submission of Budget Proposals System (OSBPS) v2.0
Hard copies generated from the OSBPS v2.0 must be submitted to the DBM in three (3) sets, duly signed and endorsed by the Department Secretary or the Head of Other Executive Office (OEO)
Hard copy submission must be the same as the encoded data under the OSBPS v2.0. If inconsistent, the OSBPS v2.0 encoding shall prevail.
All Budget Preparation (BP) Forms shall be accomplished consistent with Annex B of the FY 2024 Budget Call
4